## Product Backlog
S.No | UserStory
1 | As a customer I want to update educational document so that it can be submited as per the reqirement

## TasksSprint Backlog
UserStory | Tasks | Task | Assigned Developer | Estimation Time
1 | 1 | Create getUserIDService() to get the userID | Narshimulu | 3 Hrs
- Get the user id based on Email provided
- Check and Add the userID to the database
| 2 | Create uploadDocumentService() to upload document. | Karthik | 3 hrs
- Check weather content is avilable or not
- Check and limit the size of the file(not more than 1 MB)
- Update the file path to the database table if succesfull upload
| 3 | Create DAO classes for database table and fields
- Configure JPA/Hibernate to database.
- Create DAO class UpdateEduDoc.
| 4 | Work on REST api for creating services with maven | Srikanth Reddy | 5
- Configure JAX-RS api for services with maven dependency
- Configure TOMCAT server with maven plugin to run REST services
| 5 | DoD : | Sindhura
- Design
- Create Test cases
- Clean Code
- Refactoring
- Review and Meetings
- Documentation

## Project Status
Sprint 1 (20-Nov-2018 to 21-Nov-2018)
| Todo | In progress | Verify | Review | Closed
| Get the user id based on Email provided | TRUE | FALSE | FALSE | FALSE
| Check and Add the userID to the database | FALSE | FALSE | FALSE | FALSE
| Check weather content is avilable or not | FALSE | FALSE | FALSE | FALSE
| Check and limit the size of the file(not more than 1 MB) | FALSE | FALSE | FALSE | FALSE
| Update the file path to the database table if succesfull upload | FALSE | FALSE | FALSE | FALSE
| Configure JPA/Hibernate to database | FALSE | FALSE | FALSE | TRUE
| Create DAO class UpdateEduDoc | FALSE | FALSE | FALSE | FALSE
| Configure JAX-RS api for services with maven dependency | FALSE | FALSE | FALSE | TRUE
| Configure TOMCAT server with maven plugin to run REST services | FALSE | FALSE | FALSE | TRUE

## Test Cases
TESTCASEID | TEST CASES | SUCCESS/FAILURE | SEVERITY
T1 | Check whether userid is present in the database or not
T2 | Check whether unique URL is generated after uploading an image
T3 | Check whether you are able to retrieve exact userid based on email id provided
T4 | Verify that is there any maximum size limit of file to upload.
T5 | Verify that if any file open then that file can be uploaded or not.
T6 | Verify that same file name must be shown while uploading and same file must show after uploading.
T7 | Check whether the userid is valid userid